## Cover
Real Estate Financial Modeling
Conditional Statements Introduction
Copyright © 2009 Real Estate Financial Modeling, LLC. All rights reserved.

## Conditional Statements Intro
Using Conditional Statements to Allocate Values Over Time
Set up a timeline "Control Panel".
Event/Milestone/Activity Duration | Value |  | Month #
Project Start Date |  |  | 1
Pre-Construction (months) | 3
Construction Start |  |  | 4
Construction Duration (months) | 4
First C of O Received & First Unit Rent Commencement |  |  | 6
Construction End & Final C of O Received |  |  | 7
Post-Construction Leasing Duration (months) / Last Unit Leased | 3 | / | 10 |  | Check on Units Leased
Number of Units to Lease | 184 |  |  |  | 184
Number of Months of Leasing | 5 |  |  |  | All units are leased
Units Leased per Month | 36.8
Retail Tenant Improvement Payment |  |  | 12
Disposition (Sale) of Apartments, Parking and Retail |  |  | 12
Retail Tenant Rent Commencement |  |  | 15
Calendar Month |  |  | 2010-01-01 | 2010-02-01 | 2010-03-01 | 2010-04-01 | 2010-05-01 | 2010-06-01 | 2010-07-01 | 2010-08-01 | 2010-09-01 | 2010-10-01 | 2010-11-01 | 2010-12-01 | 2011-01-01
Month # |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13
Construction Month # |  |  | 0 | 0 | 0 | 1 | 2 | 3 | 4 | - | - | - | - | - | -
Construction Status (1=Pre, 2=Construction, 3=Post) |  |  | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 3
Calendar Year |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2
Example | Total
Development Fee (paid only during Construction) | 500000 |  | 0 | 0 | 0 | 125000 | 125000 | 125000 | 125000 | 0 | 0 | 0 | 0 | 0 | 0
Note on B23: Construction Month = IF(Current Month > Construction End month #, "-", IF(Current Month>= # of months of Pre-Construction+1, IF (Current Month = # of months of Pre-Construction,1, Last Month's Construction month #+1),0)